## ورقة1
Feasibility Analysis - Community Learning & Training Management System (CLTMS)
Type | Current Situation / Considerations | Proposed Solution / Benefits | Feasibility Result
Technical | Course and enrollment data kept in paper forms, spreadsheets and chat groups; no real-time seat availability; no central database. | Responsive web application (Arabic/English) with a MySQL/PostgreSQL database, cloud hosting, daily backups, email/SMS notifications. | ✅ Technically feasible
Operational | Manual registration is slow; queues; difficult to track payments and attendance; some staff may resist change. | Online enrollment, automatic seat control and waiting list, payment records, attendance and certificates; training and one-month parallel run. | ✅ Operationally feasible
Economic | One-time cost about EGP 250,000 (development, hosting setup, training, data migration) and about EGP 100,000 per year to run. | Benefits about EGP 270,000 in Year 1 (admin labor, paper, fewer errors, extra enrollment), growing 8% per year. See sheets ورقة2 and ورقة3. | ✅ Cost-effective (NPV ≈ EGP 478,275)
Legal | Learner personal data and payment records must be protected. | Consent, access control and encryption in line with Egypt's Personal Data Protection Law (Law 151 of 2020); licensed payment provider. | ✅ Legally feasible
Schedule | Registration and reporting depend on manual work and delay the service. | Estimated timeline about 6 months (requirements → design → development → testing/data migration → training and go-live). | ✅ Achievable timeline

## ورقة2
All amounts are planning estimates in EGP. Blue = input, black = formula. |  |  |  |  | Cost–Benefit Analysis – Community Learning & Training Management System (CLTMS) (EGP)
| Category | Description | Estimated Cost | Benefits | Estimated Value (per year)
| Software | Analysis, design, development and testing of the web system (one-time) | 180000 | Online catalog and enrollment replace manual registration and reporting. | 120000
| Hardware / hosting setup | Cloud server setup, backups, staff devices (one-time) | 30000 | Fewer enrollment and payment errors; service available all the time. | 30000
| Training | Staff and trainer workshops and user guides (one-time) | 20000 | Smooth transition; staff use the system efficiently. | Included in other benefits
| Data migration | Moving existing learner and course records from spreadsheets (one-time) | 20000 | All records available from day one. | Included in other benefits
| Maintenance and running costs | Hosting, support, licenses/SMS, administrator time (per year) | 100000 | Keeps the system reliable and secure. | -
| Administration | Current manual system: paper forms, printing, notices | - | Eliminated with CLTMS → mostly paperless. | 20000
| Enrollment revenue | Extra learners reached online (about 200 × EGP 500) | - | Wider reach and easier enrollment. | 100000
| User Experience | Queues and phone calls waste learners' time | - | Faster access to courses, better satisfaction and reputation. | Intangible but high value
| Total (first year) |  | 350000 |  | 270000
Summary
[5 empty] | Total estimated costs (first year, EGP) | 350000
[5 empty] | Total estimated annual benefits (Year 1, EGP) | 270000
[5 empty] | Payback period (years) | 1.4287
[5 empty] | Net present value over 5 years (EGP) | 478275.4839
Conclusion: CLTMS is economically feasible - it pays back in about 1.4 years and has a clearly positive 5-year NPV.

## ورقة3
5-Year Projection - CLTMS (EGP)
|  |  | Discount rate | 12%
|  |  | Annual benefit growth | 8%
|  |  | Annual operating cost growth | 5%
Assumptions are estimates; change the yellow cells to test other scenarios.
EGP | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Year index | 0 | 1 | 2 | 3 | 4 | 5
Benefits | 0 | 270000 | 291600 | 314928 | 340122.24 | 367332.0192
Development cost (one-time) | 250000 | 0 | 0 | 0 | 0 | 0
Operating costs | 0 | 100000 | 105000 | 110250 | 115762.5 | 121550.625
Total costs | 250000 | 100000 | 105000 | 110250 | 115762.5 | 121550.625
Net cash flow | -250000 | 170000 | 186600 | 204678 | 224359.74 | 245781.3942
Cumulative net cash flow | -250000 | -80000 | 106600 | 311278 | 535637.74 | 781419.1342
Discount factor | 1 | 0.89286 | 0.79719 | 0.71178 | 0.63552 | 0.56743
PV of benefits | 0 | 241071.4286 | 232461.7347 | 224159.5299 | 216153.8324 | 208434.0527
PV of costs | 250000 | 89285.7143 | 83705.3571 | 78473.7723 | 73569.1616 | 68971.089
PV of net cash flow | -250000 | 151785.7143 | 148756.3776 | 145685.7576 | 142584.6708 | 139462.9637
Payback helper (years) | 0 | 0 | 1.4287 | 0 | 0 | 0
Net present value (NPV, EGP) | Year 0: 478275.4839
Return on investment (ROI, PV basis) | Year 0: 74.27%
Internal rate of return (IRR) | Year 0: 70.12%
Payback period (years) | Year 0: 1.4287